## Bug New Requirments Report
Tester | Date | Bug / Task ID | Module | Sub_Module | Origin | Test Data | Test Env or Operating System | Steps to Reproduce | Bug Title | Bug / Task Description | Expected Result | URL | Screenshot/Video | Priority | Tester Status | Assigned to | Developer Status | Front Dev's Feedback | Back Dev's Feedback | Tester's Feedback | Bug Fix Start Date | Bug Fix End Date | Tester Testing Date | Target date | Tester Bug Close Evidence
Musbir | 2024-10-15 | BUG_CBA-001 | Trainee Questions | Search Module | Backend | Answers | Win 11 and Chrome Browser | 1. Login Chat Boat Admin 2, Go to Trainee Questions module 3.Then Go to Search Respected Answers, Put Answers in Search field and Click Answer |  | Search Answer or Filter Not working as expected, its not showing proper "Published" and "Not Publish" Questions | Questions And Answers can filter Proper "Publish" and "Not Publish" | https://chat-admin.app.cloudxperte.com/traineeQues | https://jam.dev/c/eb8cf673-c704-4ff0-8965-2d9aaaf6befd | HIGH | Closed | Aamer Shaikh | Fixed |  |  |  | 15-10-24 | 15-10-24 | 15-10-24 | 15-10-24
Musbir | 2024-10-15 | BUG_CBA-002 | Trainee Questions | Filter Question Module | Backend | Answers | Win 11 and Chrome Browser | 1. Login Chat Boat Admin 2, Go to Trainee Questions module 3.Then Go to Select Filter "ALL", "Publish" "Unpublish" |  | The Respected Filter Data Taking Time to Show its taking 25+ seconds to load | Respected Data Should be Show in less time where it will not impact on Users Experience | https://chat-admin.app.cloudxperte.com/traineeQues | https://jam.dev/c/54c5ebb0-d45e-4f83-956c-11f87a477f64 | Medium | Closed | Aamer Shaikh | Fixed |  |  | Respected Issue working fine but some time, Pagination Issue: Some time if user apply random behavior to click on Filter like All, Publish and Not Publish whenever user use Pagination to move next page that time issues Showing "No Data Found" | 15-10-24 | 15-10-24 | 15-10-24 | 15-10-24 | https://jam.dev/c/79dd08c9-a49d-464a-8015-300d7fe1863d
Musbir | 2024-11-07 | TASK_CBA-003 | Chat Bot |  | BE and FE | User Interface and File | Win 10 OS - Desktop - Chrome Browser |  |  | Validation to check special character and Blank Spaces during import, do not apply validations on Underscore _ Symbol because we are using underscore for separated the Intent words but if user put underscore _ single, in last, in first that time user having respected validations | If user importing file that time system give validations for avoid special characters and blank spaces in intents. Validations message should be "Intents cannot contain special characters or blank spaces. Please correct the data and try again." and if user put underscore _ single, in last, in first that time show validations like " |  |  | HIGH | Yet to Come | Amir Pathan | Fixed | 2024-11-08
Musbir | 2024-11-07 | TASK_CBA-004 | Chat Bot |  | BE and FE | User Interface and File | Win 10 OS - Desktop - Chrome Browser |  |  | Validation to check Intent Mapped proper as expected with separated by underscore _ like (Module_Submodule_Topic_Action) | If user importing file that time system showing for check the Intent Mapped proper as expected with separated by underscore _ like Module_Submodule_Topic_Action while Add "this is guideline , we need to put that as instruction when creating, update intent" - This all show on Tooltip Tooltip - "Ensure that the Intent is properly mapped according to the naming convention: Module_Submodule_Topic_Action" |  |  | HIGH | Yet to Come | Amir Pathan | Fixed | 2024-11-08
Musbir | 2024-12-03 | TASK_CBA-005 | Chat Bot Admin | Un Answered List and Conversations |  |  | Win 10 OS - Desktop - Chrome Browser |  |  | Storing Duplicate data in Un Answered data and Conversations, whenever user asking same questions | Show Unique Questions in Un Answered List | http://wifiattendencefront.app.redbytes.in/unAnsweredListing | https://jam.dev/c/5fd22c9b-22bd-4f94-813f-8aa91f2fe241 https://jam.dev/c/f163426c-961c-4caf-94b8-143f3606b261 |  | Yet to Start |  | New
Musbir | 2024-12-17 | TASK_CBA-006 | Chat Bot Admin | Import Training Question List |  |  | Mac PC - Desktop - Chrome Browser |  |  | Unable to import question and answer file in chat bot. | file should be upload and all respected questions shows | https://app.wifiattendance.com/traineeQues | https://jam.dev/c/02c7c6dc-fa79-45b6-be0c-e37f106a14f6 | HIGH | Yet to Start |  | New
Musbir | 2024-12-17 | TASK_CBA-007 | Chat Bot Admin | Data Statistics |  |  | Mac PC - Desktop - Chrome Browser |  |  | Unable to upload Submodule Icons and not showing images on icons | user must upload icons and all respected images shows on applications | https://app.wifiattendance.com/dataStatistics | https://jam.dev/c/96783f78-d6cf-49a8-bafc-97a2dedfa207 |  | Yet to Start |  | New
Musbir | 2024-12-17 | TASK_CBA-008 | Chat Bot Admin | conversation flow |  |  | Mac PC - Desktop - Chrome Browser |  |  | having issue to get map module and related module on UI, but its mapped in Back end side |  | http://wifiattendencefront.app.redbytes.in/converstionflow |  |  | Yet to Start |  | New
Musbir | 2024-12-17 | TASK_CBA-009 | Chat Bot Admin | Setting - Access |  |  | Mac PC - Desktop - Chrome Browser |  |  | Please add the Down Arrow on labels of Modules | If we add the down arrow on labels of access it can be easy to understand users to click on it to check submodules list. | http://wifiattendencefront.app.redbytes.in/accesscode | https://jam.dev/c/62207d01-5d53-478d-b1db-c66c34e4b311 |  | Yet to Start |  | New
Musbir | 2024-12-17 | TASK_CBA-0011 | Chat Bot Admin | Impot Training Data and add Questions |  |  | Mac PC - Desktop - Chrome Browser |  |  | When user Import file with added data like question, Answers, Module Submodule, Intent, Actions, Topic so in that file if user mapped same Submodule with different Module that time in chat bot admin those submodule not showing, so we need validations for that user not upload or add same/duplicate submodules and module too. | User should not add duplicate modules and submodules if there is condition to added duplicate so please be add those data in system and show it. |  |  |  | Yet to Start |  | New
Musbir | 2024-12-26 | TASK_CBA-0012 | Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | UI Issue - if user scroll last that time background page getting scroll even the pointer stick on Chat bot, and Last question not visible its showing back in "Type your message" text area | all respected questions and answer must be show to user and scroll proper. | https://www.vehicletracking.qa | https://jam.dev/c/6b4df77d-29aa-4f67-b10f-639dae8a8ff7 |  | Yet to Start |  | New
Musbir | 2024-12-26 | TASK_CBA-0013 | Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | If user complete the ask questions limit iver chat bot then the login form open, there User need Back or Close Button on that form, and there is spelling mistake for Please enter password validation | user have better user interface for better experience, and do not have any spelling mistakes. | https://www.vehicletracking.qa/ | https://jam.dev/c/0f4eda46-7c5c-455a-8d71-83efceab185a |  | Yet to Start |  | New
Musbir | 2024-12-26 | TASK_CBA-0014 | Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | on Login Page, we have Forg Forget password? or Sign up link both link not working, user not able to click and navigate on respected page. | Forget password? or Sign up should be click or working fine for further actions. | https://www.vehicletracking.qa/ | https://jam.dev/c/f9599f48-a75a-4433-bd35-2d307b1b081c |  | Yet to Start |  | New
Musbir | 2024-12-26 | TASK_CBA-0015 | Chat Bot Admin | Data Statistics Page - Submodule |  |  | Mac PC - Desktop - Chrome Browser |  |  | Add Illustration icon default image getting crash, Default + plus sign image not display if user edit, and save without adding the Illustration. | Respected Images should be displayed over changes done | http://wifiattendencefront.app.redbytes.in/submoddataStat/DeliveryApp | https://jam.dev/c/f3949600-bd48-4177-b019-78fd6ffee9f7 |  | Yet to Start |  | New
Musbir | 2024-12-26 | TASK_CBA-0016 | Chatbot - Live | ChatBot Live site |  |  | Mac PC - Desktop - Chrome Browser |  |  | Facing issue for Live Chat bot while Testing new data I found that the page keep loading and API getting failed that time | Chatbot should be working fine |  | https://jam.dev/c/eafbd83a-b45b-4b1a-b7a9-db31ea6bfa67 |  | Yet to Start |  | New
Musbir | 2024-12-27 | TASK_CBA-0017 | Chat Bot QA site | On Chat bot |  |  | Mac PC - Desktop - Chrome Browser |  |  | If user open https://www.vehicletracking.qa site then chatbot option show, in that user type directly any questions without "Start Again" that time those questions entered but not show any response to user showing same page, after that if user click on "Start Again" button then those entered question and answers appear. also user need to scroll left and right icon over chat bot for Module and Submodule. | Before Start again chatbot not take questions until user start again the chat bot, or user need scroll left right icon to know the all modules and Submodule. | https://www.vehicletracking.qa/ | https://jam.dev/c/422158fd-e100-4408-809b-2da58276fe65 |  | Yet to Start |  | New
Musbir | 2024-12-30 | TASK_CBA-0018 | Chat Bot - Live site | On Chat bot Live |  |  | Mac PC - Desktop - Chrome Browser |  |  | Issue with Live chat bot if user select one module or type question for one respected module, then chat bot showing another modules question in Suggestions, expected there show the selected module or submodule. Questions in the Suggestions | Expected there show the respected selected module or submodule. Questions in the Suggestions because user have the intent to ask question so we should show the respected suggestions | https://www.vehicletracking.live | https://jam.dev/c/1caf0fb7-2303-4633-b3db-6f112b9dfdc8 |  | Yet to Start |  | New
Musbir | 2024-12-30 | TASK_CBA-0019 | Chat Bot Admin | Data Statistics Page - Module |  |  | Mac PC - Desktop - Chrome Browser |  |  | Issue with Update the Module Icons, while updated icons the icon replicate to another module | show respected icons on the module | http://wifiattendencefront.app.redbytes.in/dataStatistics | https://jam.dev/c/d06a1469-62b2-46ca-b2c1-18a02424b9ba |  | Yet to Start |  | New
Musbir | 2024-12-30 | TASK_CBA-0020 | Chat Bot Live |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | Showing Wrong link to respected submodule when use click on module and submoule then click to questions that time we show the answers with there page link. | show the respected page link with answers | https://www.vehicletracking.live/ | https://jam.dev/c/8e4f01dc-ac2b-49c4-94d1-e9784499e195 |  | Yet to Start | Ashu Ojha | New
Musbir | 2025-01-10 | TASK_CBA-0021 | Chat Bot Admin | Data Statistics Page - Submodule-Intent page |  |  | Mac PC - Desktop - Chrome Browser |  |  | Showing the old Mapped intent in submodule if user updated the file uploading the new data with that submodule with repected intent, so need to Delete option over the intent page where it can be delete from database. | show the respected data | https://app.wifiattendance.com/topics/DispatchCustomer | https://jam.dev/c/aa479513-c44e-4d08-9d47-4e0be413c230 |  | Yet to Start |  | New
Musbir | 2025-01-13 | TASK_CBA-0022 | Live Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | Issue for suggestions questions showing the duplicate. | do not show duplicates questions in suggestions | https://www.vehicletracking.live/ | https://jam.dev/c/e3067c14-6ae4-4b67-a596-c21fdaaa48a6 |  | Yet to Start |  | New
Musbir | 2025-01-13 | TASK_CBA-0023 | Live Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | Showing the wrong submodule when user ask question and the question is for Dashboard map, But in answer its showing the App feature submodule, routes is correct | do not show wrong data | https://www.vehicletracking.live/ | https://jam.dev/c/b6acac98-6f9c-48be-98d0-68b1dc3e6620 https://jam.dev/c/81b86b2e-b2e9-4a3a-9c25-8b60e4a60d08 |  | Yet to Start |  | New
Musbir | 2025-01-13 | TASK_CBA-0024 | Live Chat Bot |  |  |  | Mac PC - Desktop - Chrome Browser |  |  | If user enter anything those data not in present in this case the chat bot showing the "Suggested question, and Screen. | do not show the screen and sugessted questions if the entered questions is not present in the data. | https://www.vehicletracking.live/ | https://jam.dev/c/71f9d096-e738-40a0-b0b3-1f4a8364dd5f |  | Yet to Start |  | New
Musbir | 2025-01-13 | TASK_CBA-0025 | Chat Bot - Live site | Data Statistics Page - Module |  |  | Mac PC - Desktop - Chrome Browser |  | in ChatBot Admin Icons update not Working as expected | in ChatBot Admin Icons update not Working as expected, if user change the icon from Datastatics page then those icons reflect on the live chat bot, this case not working as expected | Respected Icons should be display once updated by users | https://www.vehicletracking.live/ | https://jam.dev/c/c6eff7d3-4ba8-491d-b861-7badcc581281 |  | Yet to Start |  | New

## VT Mobile Customer APP-Bug Shee
Tester | Date | Bug / Task ID | Module | Sub_Module | Origin | Test Data | Test Env or Operating System | Bug Title | Bug / Task Description | Expected Result | URL | Screenshot/Video | Priority | Tester Status | Assigned to | Developer Status | Front Dev's Feedback | Back Dev's Feedback | Tester's Feedback | Bug Fix Start Date | Bug Fix End Date | Tester Testing Date | Target date | Tester Bug Close Evidence
Musbir | 2024-10-15 | VTCApp-001 | ChatBot | Sub_Modules |  |  | ISO Mobile - MAC device and Chrome Browser | Submodules Icon not prsent | during the tesitng for all module sub module verify the chatbot open properly and show the respected question and answer based on modules submodules. here issue for submodule Icon | Show all respected icons in the chatbot | https://jam.dev/c/dcf3771b-1204-4a52-a44a-486720c0ba35 |  | HIGH | Yet to Come |  | New
Musbir | 2024-10-15 | VTCApp-002 | ChatBot | Questons and answers |  |  | ISO Mobile - MAC device and Chrome Browser | Suggestions Questions showiug | when user ask module deleted question answer will display correct but showing another module Suggestions question: | Show all respected suggestions with respected module | https://jam.dev/c/7fb62e51-9171-4e96-b6cc-0d68221d410d |  | HIGH | Yet to Come |  | New

## R1-CR Points
Release 1
Requirement ID | Req. Date | Req. Title | Req. Descriptions | Review By | Approved By | Approval Date | Priority | Level Of Priority | Req. Status | Developer | Development Status | Development End Date | Development Total ETA | Dev Feedback | Tester | Testing Status | Testing Date | Testing Total ETA | Tester Feedback | Plan Target - End Date | Closed Evidence Urls
CB-Req-0001 | 18-12-2024 | Add Image Ilustraion for Submodule | In Chat Bot Admin user can add, Update, Delete the Illustraion (Images), where that will be show on Live Chat Bot when user ask question then chat bot will show the answer with the respected Illustraion, the Illustraion will be apply onSubModule only. | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan, Amer Shaikh | Completed |  |  |  |  | Yet to Come
CB-Req-0002 | 18-12-2024 | on Chat Bot show the PDF file | If user login that time data will be present in PDF file otherwise the report formate show with some default data to understnad the user, user can see the files not get donwload, PDF have the content and Image of screenshots for respected page which is mapped with question nd answer. | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed |  | Yet to Start |  |  |  |  | Yet to Come
CB-Req-0003 | 18-12-2024 | show the Module Name on Submodule Page | If user move to Submodule page after click on module that time on submodule page the module name will be show | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan | Completed |  |  |  |  | Yet to Come
CB-Req-0004 | 18-12-2024 | in Data Stastics Make new screen for Topic same as module and submodule | User Click on Module then its navigate to Sub Module page after that user click on Submodule then the topics will be show in next page, page have same features like prev, Edit, Add icon, Add, Image. | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan, Amer Shaikh | Completed |  |  |  |  | Yet to Come
CB-Req-0005 | 18-12-2024 | User can Like or Dislike Answer on Live chatbot | User have feature to like dislike on answers while chatting on live chatbot | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan, Amer Shaikh | Completed |  |  |  |  | Yet to Come
CB-Req-0006 | 18-12-2024 | Add new module in Chatbot for users feedback like "Answer Feedback" | When user give feedback on answer either like or Dislike those data will show on the Answer Feedback page, its a seprate module on the navigations | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan, Amer Shaikh | Completed |  |  |  |  | Yet to Come
CB-Req-0006 | 18-12-2024 | Remove duplication of suggested question from live chat bot | Remove duplication of suggested question from live chat bot when user click and chat bot give the respected answer of that questions, that time do not show same question again to user in suggestions. | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Shaikh | In Progress |  |  |  |  | Yet to Come
CB-Req-0002 | 18-12-2024 | on live Chat Bot show the Image Illustraion | In Chat Bot Admin user can add Illustraion (Images), that will be show on Live Chat Bot when user ask question then chat bot will show the answer with the respected Illustraion, the Illustraion will be apply onSubModule only. | Sameer Sir | Sameer Sir | 18-12-2024 | High | 1st | Completed | Amer Pathan, Amer Shaikh | Completed |  |  |  |  | Yet to Come